## Log
Date | ID | Title | Type | Status | Evidence / Notes
2026-08-10 | M0 Phase 0 | Environment and governance | Milestone | DONE (Epic 0 tickets) | ENV-001..005, LEGAL-001, ARCH-001 all DONE. Gate A partial. Human M0 sign-off still required before Epic 1 per Docs/Tickets.md milestone table.
2026-08-10 | ENV-004 | Discover build/test/cook/package commands | ENV | DONE | 427/427 Smoke tests at close (2026-08-12). BuildCookRun archive verified.
2026-08-10 | ENV-005 | Verify local Unreal MCP, generate client config | ENV | DONE | Loopback-only confirmed; 7 non-loopback IPs refused.
2026-08-12 | CORE-001 | Module/folder structure and logging categories | CORE | DONE | code-reviewer approved at 9a7d5d4 after 2 blockers closed. 4 findings (N-1,N-3,N-6,N-7) deferred to CORE-002.
2026-08-13 | CORE-002 | Settings, build ID, units, telemetry contracts | CORE | DONE | code-reviewer approved across 2 passes at f84300c. test-engineer confirmed 432/432 Smoke tests, both targets clean. Merged to main at 358848b.
2026-08-14 | RACE-001 | Race state machine and monotonic clock | RACE | DONE | code-reviewer approved across 2 passes at 7832d0a. test-engineer independently confirmed 442/442 Smoke tests from a from-scratch rebuild. Merged to main at 2c41989.

## Tickets
Epic | ID | Title | Owner | Depends on | Gate | Status
Epic 0 -- environment & governance | ENV-001 | Record engine/toolchain/worker/browser matrix | director | - | A | DONE
Epic 0 -- environment & governance | ENV-002 | Source control, LFS/locks, ignore rules, clean-clone test | director | - | A | DONE (locks inert -- BLOCKER-002)
Epic 0 -- environment & governance | ENV-003 | Enable/verify plugins and production exclusions | director | ENV-001 | A, G | DONE
Epic 0 -- environment & governance | ENV-004 | Discover build/test/cook/package commands | director | ENV-003 | A | DONE
Epic 0 -- environment & governance | ENV-005 | Verify local Unreal MCP, generate client config | director | ENV-003 | G | DONE
Epic 0 -- environment & governance | LEGAL-001 | Inventory/quarantine assets, initialize ledger | ip-compliance-auditor | - | H | DONE (5 open legal questions)
Epic 0 -- environment & governance | ARCH-001 | Pixel Streaming 2 + scaling ADR | director | ENV-001 | - | DONE (ADR-0001..0004)
Epic 1 -- project skeleton | CORE-001 | Module/folder structure and logging categories | director | ENV-004 | A | DONE
Epic 1 -- project skeleton | CORE-002 | Settings, build ID, units, telemetry contracts | race-systems-engineer | CORE-001 | A, B | DONE
Epic 1 -- project skeleton | TEST-001 | Test module and first smoke test | test-engineer + implementer | CORE-001 | A | DONE (merged 5506dcf)
Epic 1 -- project skeleton | CORE-003 | DataAsset validation framework | race-systems-engineer | CORE-002 | A | DONE (merged 7596b9e)
Epic 2 -- vehicle graybox | VEH-001 | Keyboard/gamepad input mappings | vehicle-physics-engineer | CORE-001 | B | OPEN
Epic 2 -- vehicle graybox | VEH-002 | Prototype chassis/wheels/collision, Chaos baseline | vehicle-physics-engineer | VEH-001 | C | OPEN
Epic 2 -- vehicle graybox | VEH-003 | Engine/transmission/diff/brakes/steering/suspension tune data | vehicle-physics-engineer | VEH-002, CORE-003 | C | OPEN
Epic 2 -- vehicle graybox | VEH-004 | Telemetry and failure detection | vehicle-physics-engineer | VEH-002 | C | OPEN
Epic 2 -- vehicle graybox | VEH-005 | Camera and safe reset | vehicle-physics-engineer | VEH-002 | B, C | OPEN
Epic 2 -- vehicle graybox | VEH-006 | Recorded manoeuvre tests and 30-minute soak | test-engineer + implementer | VEH-003..005 | C | OPEN
Epic 3 -- track and race | TRACK-001 | Original circuit graybox and spline centerline | race-systems-engineer | CORE-001 | B | DONE (merged 5d44744)
Epic 3 -- track and race | TRACK-002 | Ordered checkpoint gates and crossing direction | race-systems-engineer | TRACK-001 | B | OPEN
Epic 3 -- track and race | RACE-001 | Race state machine and monotonic clock | race-systems-engineer | CORE-002 | B | DONE
Epic 3 -- track and race | RACE-002 | Lap/sector/progress/validity logic | race-systems-engineer | TRACK-002, RACE-001 | B | OPEN
Epic 3 -- track and race | RACE-003 | Results, restart, metadata | race-systems-engineer | RACE-002 | B | OPEN
Epic 3 -- track and race | RACE-004 | Shortcut/reverse/double-trigger/reset automation matrix | test-engineer + implementer | RACE-003 | B | OPEN
Epic 4 -- HUD | UI-001 | HUD view model and data contract | race-systems-engineer | RACE-003 | B | OPEN
Epic 4 -- HUD | UI-002 | Speed/RPM/gear/lap/time/delta/countdown/results | race-systems-engineer | UI-001 | B | OPEN
Epic 4 -- HUD | UI-003 | Input prompts, settings, restart flow, accessibility baseline | race-systems-engineer | UI-002 | B | OPEN
Epic 4 -- HUD | UI-004 | HUD functional and screenshot tests | test-engineer + implementer | UI-003 | B, D | OPEN
Epic 5 -- Pixel Streaming | STREAM-001 | Local packaged PS2 connection | pixel-streaming-engineer | ENV-004, UI-002 | F | OPEN
Epic 5 -- Pixel Streaming | STREAM-002 | Browser frontend shell, versioned custom messages | pixel-streaming-engineer | STREAM-001 | F, G | OPEN
Epic 5 -- Pixel Streaming | STREAM-003 | Gamepad/focus/reconnect tests | test-engineer + implementer | STREAM-002 | F | OPEN
Epic 5 -- Pixel Streaming | STREAM-004 | External STUN/TURN test | pixel-streaming-engineer | STREAM-002 | F | BLOCKED (BLOCKER-001)
Epic 5 -- Pixel Streaming | STREAM-005 | Session broker/worker lifecycle spike | pixel-streaming-engineer | STREAM-002 | G | BLOCKED (BLOCKER-001)
Epic 5 -- Pixel Streaming | STREAM-006 | WebRTC telemetry and latency measurement | performance-engineer | STREAM-002 | E, F | BLOCKED (BLOCKER-001)
Epic 6 -- visual vertical slice | ART-001 | Hero car source and provenance | rendering-tech-artist | - | D, H | BLOCKED (BLOCKER-001)
Epic 6 -- visual vertical slice | ART-002 | Car material family and turntable benchmark | rendering-tech-artist | ART-001 | D | BLOCKED (BLOCKER-001)
Epic 6 -- visual vertical slice | ART-003 | Hero circuit sector and environment materials | rendering-tech-artist | - | D | BLOCKED (BLOCKER-001)
Epic 6 -- visual vertical slice | ART-004 | Lighting/post/camera benchmark | rendering-tech-artist | - | D | BLOCKED (BLOCKER-001)
Epic 6 -- visual vertical slice | ART-005 | Audio vertical slice | rendering-tech-artist | - | D | BLOCKED (BLOCKER-001)
Epic 6 -- visual vertical slice | PERF-001 | Reference trace, budgets, optimization | performance-engineer | - | E | BLOCKED (BLOCKER-001)
Epic 6 -- visual vertical slice | VIS-001 | Screenshot baseline and human art gate | rendering-tech-artist | - | D | BLOCKED (BLOCKER-001)
Epic 7 -- hardening and deployment | OPS-001 | Worker image | - | - | G | BLOCKED (BLOCKER-001)
Epic 7 -- hardening and deployment | OPS-002 | Auth, rate limit, timeout, cost guardrails | - | - | G | BLOCKED (BLOCKER-001)
Epic 7 -- hardening and deployment | OPS-003 | Metrics/logs/crashes/alerts | - | - | G | BLOCKED (BLOCKER-001)
Epic 7 -- hardening and deployment | OPS-004 | 100-cycle session test | - | - | F, G | BLOCKED (BLOCKER-001)
Epic 7 -- hardening and deployment | SEC-001 | Exposure and secret audit | - | - | G | BLOCKED (BLOCKER-001)
Epic 7 -- hardening and deployment | REL-001 | Full A-H gate report and rollback drill | - | - | A-H | BLOCKED (BLOCKER-001)

## Milestones
Milestone | Contents | Gates | Human approval | Status
M0 Phase 0 | Epic 0 | A (partial) | Required before Epic 1 | Epic 0 tickets DONE; human M0 sign-off not yet recorded
M1 Graybox | Epics 1-4 | A, B, C | Required | IN PROGRESS -- CORE-001, CORE-002, RACE-001 DONE; CORE-003, TRACK-001 in progress; rest OPEN
M2 Local streaming | Epic 5 (001-003) | F (partial) | Required | NOT STARTED
M3 Visual slice | Epic 6 | D, E | Required -- art director | BLOCKED (BLOCKER-001)
M4 Release readiness | Epic 7 | A-H | Required -- legal + ops + art | BLOCKED (BLOCKER-001)